## Sheet1
Major Activities
IEEE Infocom 2002
June 23 – 28, 2002
Color Key
| to be done | Program Chairs
| in process | Panel Chairs
| done | Tutorial Chairs
| Overdue | Publicity Chairs
Internet Chairs
Information System
Publication Chairs
Local arrangement chair
Before meeting
Guide | Activity | Responsible Party(s) | Date Due
| Hotel contract prepared & signed | Computer Society | 2000-05-12
| Committee members identified | General chair | 2000-06-10
| Publicity plans- Outline the process | Publicity chairs | 2000-06-20
| Internet connection/ Tentattive budget | Internet chair | 2000-07-01
| Publication plans- Start the process | Publication chairs | 2000-07-01
| Publication plans- Tentative budgets | Publication chairs | 2000-07-01
| Publicity plans- Tentative budget | Publicity chairs | 2000-07-01
| Budget preparation | General +Financial chair | 2000-07-10
| Budget submission | Harvey Freeman | 2000-07-15
| Call for papers- Closing | Program chair | 2000-08-06
| Papers to TPC for review request | Program chair | 2000-08-07 | 2000-08-08
| Papers distributed to TPC members | Program chair | 2000-08-10
| Prepare call for papers-Start the process | Program chair | 2000-09-01
| TPC guidelines- Start the process | Program chair | 2000-09-01
| Prepare call for papers-Complete | Program chair | 2000-12-01
| Publicity (call for papers), e-mail lists, bb | Publicity chairs | 2001-01-01
| Give-aways in Infocom’2001 | Vice chair | 2001-01-01
| Open bank account (usa) | Financial chair | 2001-02-01
| Publicity call for papers | International vice chair | 2001-02-01
| Publication (call for papers), magazines, etc | Publication chairs | 2001-02-01
| Publicity plans- Finalize the process | Publicity chairs | 2001-02-01
| E-mail CFP (1st) | Publicity/International chair | 2001-02-08
| Budget approval | Computer+Commun. Soc. | 2001-04-01
| Promote local attendance | Local arrangement chair | 2001-04-01 | 2002-06-01
| Publication plans- Finalize | Publication chairs | 2001-04-01
| Paper solicitation | International vice chair | 2001-04-08
| Committee meeting | General chair | 2001-04-24
| Establish paper tracking procedures | Program chair | 2001-04-24
| TPC guidelines- Finalize | Program chair | 2001-04-24
| E-mail CFP (2nd) | Publicity/International chair | 2001-04-26
| Solicit corporate partners | Corporate Partners chair | 2001-05-01
| Apply for NSF grant | Financial chair | 2001-05-01
| TPC membership- Start the process | Program chair | 2001-05-01
| TPC membership- Finalize | Program chair | 2001-05-01
| E-mail CFP (3rd) | Publicity/International chair | 2001-07-07
| Panels selection | Panel chair | 2001-07-09
| Tutorials selection | Tutorial chairs | 2001-07-09
| E-mail CFP (last) | Publicity/International chair | 2001-07-24
| Keynote speaker selected | Exec Committee/Vice Chairs | 2001-08-01
| IEEE Insurance | Vice chair | 2001-08-01
| Paper review- Process starts | Program chair | 2001-08-10
| Contact booksellers | Vice chair | 2001-09-01
| Attendance solicitation | International vice chair | 2001-10-01 | 2002-06-01
| Design internet connection | Internet chair | 2001-10-01
| Finalize panels | Panel chair | 2001-10-01
| Mailing lists for advanced program | Publicity chair with CS | 2001-10-01
| Finalize tutorials | Tutorial chairs | 2001-10-01
| E-mail CFP(articipation) (1st) | Publicity/International chair | 2001-10-13
| Prepare accommodation form | General chair with Hilton | 2001-10-15
| Prepare tours form | General chair with Hilton | 2001-10-15
| Initial material for advanced program | Publicity chairs | 2001-10-15
| Prepare registration form | Registration chair with CS | 2001-10-15
| Paper review- Complete | Program chair | 2001-10-24
| Initial draft of advanced program | CS | 2001-10-25
| Reviews made available to authors | Program chair | 2001-10-29
| Review of local arrangements | Local arrangement chair | 2001-11-01
| Publicity to IEEE publications | Publicity chairs | 2001-11-01
| Rebuttals due | Program chair | 2001-11-09
| Program committee meeting | Program chair | 2001-11-17 | 2001-11-18
| Executive committee meeting (NY) | General chair | 2001-11-18
| Author notification and tentative program | Program chair | 2001-11-21
| Advanced program to mailing house | CS | 2001-11-24
| E-mail CFP(articipation) (2nd) | Publicity/International chair | 2001-11-29
| Prepare internet connection | Internet chair | 2001-12-01 | 2002-06-20
| Advance program to CS | Program+Publicity chair | 2001-12-03
| Advanced program sent - outside US | CS | 2001-12-05
| Advance program from CS, 1st draft | Program+Publicity chair | 2001-12-07
| Advance program to CS | Program+Publicity chair | 2001-12-11
| Advance program from CS, 2nd draft | Program+Publicity chair | 2001-12-14
| Advance program to CS, final approval | Program+Publicity chair | 2001-12-17
| Final version of papers due (soft) | Program chair | 2001-12-27
| Advanced program sent - inside US | CS | 2001-12-28
| Tutorials contracts signed | Tutorial chairs | 2002-01-01
| Final version of papers due (hard) | Program chair | 2002-01-07
| Executive committee meeting (NY) | General chair | 2002-01-09
| Prepare conference at a glance | Program chair | 2002-01-18
| Final papers due IEEE; advancd program | Program chair | 2002-01-23
| Student grant decisions | Financial chair | 2002-02-01
| Camera ready (accepted papers) due | Publication chairs | 2002-02-01
| Proceedings/CD to printers | Publication chairs | 2002-02-01
| E-mail CFP(articipation) (3rd) | Publicity/International chair | 2002-02-10
| E-mail CFP(articipation) (4th) | Publicity/International chair | 2002-02-17
| Choose best paper | Program chair | 2002-03-01
| Victory dinner plans | Local arrangement chair+Program | 2002-03-01
| Advance registration | Computer Society | 2002-03-04
| Souvenirs | Local arrangement chair | 2002-04-01
| Session rooms assignment | Local arrangement+Program chair | 2002-04-01
| E-mail CFP(articipation) (5th) | Publicity/International chair | 2002-04-07
| Final program | Program+Publicity chair | 2002-04-10
| Send final program to printer | CS | 2002-04-18
| Advance registration closes | Computer Society | 2002-05-01
| Audio/visual | Local arrangement chair | 2002-05-01
| Badges | Registration | 2002-05-01
| Tutorials notes to printer | Tutorial+Publication Chairs | 2002-05-01
| E-mail CFP(articipation) (last) | Publicity/International chair | 2002-05-23
| Finalize internet connection | Internet chair | 2002-06-01
| Arrange video recording | Internet chair | 2002-06-01
| Finalize reception menu | Local arrangement chair | 2002-06-01
| Meetings room assignment | Local arrangement chair | 2002-06-01
| Hotel food quantity estimate | Local arrangement chair | 2002-06-15
| Hotel food quantity guaranteed | Local arrangement chair | 2002-06-20
| Proceedings/CD delivered to site | Registration+Publication chair | 2002-06-20