SIPcomm  M E M O

ephone 2.2 Manufacturing Activties Schedule At ppi-TimeZero

Following is the initial manufacturing activities chart showing activities, schedule and responsibilities for the manufacture of 100 ephone 2.2 units at ppi-TimeZero. This was developed at the kick-off meeting at ppi-TimeZero on July 27,2000.

| ACTIVITY | RESPONSIBILITY | START DATE | FINISH DATE |
| --- | --- | --- | --- |
| 1) Complete revised Gerber file (revision # 6 ) | M.Keating/TriTec |  | 8/02/00 |
| 2) Complete revised schematics (revision # 6 ) | M.Keating/TriTec |  | 7/27/00 |
| 3) Complete bill of materials (revision #6) | M.Keating |  | 8/03/00 |
| 4) Sourcing of PCB bare board materials | ppi-TimeZero |  | In stock |
| 5) Sourcing of readily available components to be populated onto the PCB | ppi-TimeZero | 7/24/00 | 8/11/00 |
| 6) Sourcing of obsolete and long lead time components to be populated onto the PCB | M.Keating | 6/ /00 | 7/27/00 |
| 7) Sourcing of 100 Sprint phone cases Model 903 | H.Weinreb | 6/ /00 | In progress, 35 on hand |
| 8) Sourcing of materials for phone case modifications | M.Keating /ppi-TimeZero |  | 8/11/00 |
| 9) Fabrication of the initial 5 PCB's (bare boards) | ppi-TimeZero | 8/03/00 | 8/18/00 |
| 10) QC Continuity test of initial 5 PCB's (bare boards) | ppi-TimeZero | 8/03/00 | 8/18/00 |
| 11) Mounting components onto initial 5 PCB's | ppi-TimeZero | 8/21/00 | 8/24/00* |
| 12) Application software (stack) and emulators | Gautam Nair / M.Keating |  | Needed by 8/18/00* |
| 13) Adapters for installing application software | ppi-TimeZero |  | Needed by 8/18/00* |
| 14) Altera software disc | Gautam Nair/ M.Keating |  | Needed by 8/18/00* |
| 15) Installing (burning-in) software at ppi-TimeZero | M.Keating/ppi-TimeZero | 8/21/00 | 8/31/00 |
| 16) Protocol for QC test of populated PCB | M.Keating |  | Needed by 8/21/00 |
| 17) QC testing of the initial 5 populated PCB's | M.Keating/N.Younger/ppi-TimeZero | 8/25/00 | 8/31/00 |
| 18) Rework | ppi-Timezero |  | As required |
| 19) Disassembly and modification of initial 5 Sprint phone cases | N.Younger/Keating/ ppi-TimeZero | 8/30/00 | 8/31/00 |
| 20) Assembly of initial 5 ephone 2.2 units | N.Younger/Keating/ ppi-TimeZero | 9/05/00 | 9/08/00 |
| 21) Protocol for testing ephone 2.2functions | M.Keating/Howe Digital |  | 9/08/00 |
| 22) Functional test of initial 5 ephone 2.2 units | SIPComm/M.Keating/N.Younger | 9/11/00 | 9/15/00 |
| 23) Packaging of completed 5 ephone 2.2 units ** | N.Younger/ppi-TimeZero |  | 9/22/00** |
| 24) Revise disassembly/modification/assembly instructions | N. Younger | 9/05/00 | 9/15/00 |
| 25) Fabrication of the next 95 PCB bare boards | ppi-TimeZero | 9/05/00 | 9/22/00 |
| 26) QC/Continuity test of the 95 PCB bare boards | ppi-TimeZero | 9/05/00 | 9/22/00 |
| 27) Mountingcomponents onto the 95 PCB's | ppi-TimeZero | 9/25/00 | 10/04/00 |
| 28) QC testing of the 95 populated PCB's | M.Keating/N.Younger/ppi-TimeZero | 10/05/00 | 10/11/00 |
| 29) Rework | ppi/TimeZero | 10/05/00 | As required |
| 30) Disassembly and modification of the 95 Sprint phone cases | ppi-TimeZero | 9/25/00 | 10/05/00 |
| 31) Assembly of the 95 ephone 2.2 units | ppi-TimeZero | 10/05/00 | 10/13/00 |
| 32) Functional testing of the 95 ephone 2.2 units | SIPComm/M.Keating/N.Younger | 10/05/00 | 10/20/00 |
| 33) Rework | ppi-TimeZero |  | As required |
| 34) Packaging of the completed 95 ephone units | ppi-TimeZero | 10/09/00 | 10/27/00 |

*It is planned to install the software in the Altera and the AMD ROM chips before these chips are mounted on the PCB. Provision has been made for a later installation or change at an additional delay and cost.

** The cartons that came with the original Sprint telephones will be reused to package the individual ephone 2.2 units. However, the cartons need to be reworked with descriptive material relative to the ephone 2.2 . Also, SIPComm needs to resolve what will be shown on the carton relative to FCC compliance. Nita Younger will handle design and preparation of the printed self adhering overlays.

HGW;ephone 2.2  Manufacturing Activities Schedule,7/28/00